## Worksheet
Activity | Start Date | End Date | Responsible Party | Budget Allocation (USD) | Status | Cost Variance
Project Initiation | 01/01/2024 | 01/31/2024 | Project Manager | 5,000.00 | On Track | $0.00
Feasibility Study | 02/01/2024 | 02/15/2024 | Business Analysts | 8,500.00 | On Track | $150.00
Design Phase | 03/01/2024 | 04/30/2024 | Design Team | 35,000.00 | On Track | $2,300.00
Development Phase | 05/01/2024 | 08/31/2024 | Engineering Team | 75,000.00 | On Track | $1,850.00
Testing & QA | 09/01/2024 | 10/31/2024 | QA Department | 12,500.00 | On Track | $320.00
Deployment & Go-Live | 11/01/2024 | 11/30/2024 | IT Operations | 6,000.00 | On Track | $50.00
Post-Implementation Review | 12/01/2024 | 12/31/2024 | Project Manager & Finance | 3,500.00 | On Track | $280.00