## Worksheet
Task | Start Date | End Date | Responsible Person | Budget Allocation (USD) | Actual Spend (USD) | Status
Project Initiation & Planning | 2024-03-01 | 2024-03-15 | John Doe | $15,000 | $14,800 | On Track
Resource Acquisition & Setup | 2024-03-16 | 2024-04-10 | Jane Smith | $25,000 | $24,500 | On Track
Design & Prototyping Phase | 2024-04-11 | 2024-05-30 | Mike Johnson | $35,000 | $33,800 | On Track
Development & Testing | 2024-06-01 | 2024-07-31 | Sarah Lee | $75,000 | $73,950 | On Track
Deployment & Training | 2024-08-01 | 2024-08-31 | David Kim | $15,000 | $15,120 | Over Budget (Minor)
Post-Implementation Review | 2024-09-01 | 2024-09-15 | All Team Members | $5,000 | $4,850 | On Track