## Worksheet
Task | Start Date | End Date | Responsible Party | Budget Allocation (USD) | Actual Cost (USD) | Variance (USD) | Status
Project Initiation | 2024-01-15 | 2024-01-30 | Project Manager | 5,000.00 | 4,800.00 | 200 | On Track
Requirements Gathering | 2024-02-01 | 2024-03-15 | Business Analysts | 15,000.00 | 14,750.00 | 250 | On Track
Design & Planning | 2024-03-16 | 2024-04-30 | Design Team | 25,000.00 | 24,950.00 | 50 | On Track
Development Phase | 2024-05-01 | 2024-07-31 | Engineering Team | 120,000.00 | 118,500.00 | +1,500.00 | On Track
Testing & Quality Assurance | 2024-08-01 | 2024-08-31 | QA Team | 20,000.00 | 19,850.00 | 150 | On Track
Deployment & Go-Live | 2024-09-01 | 2024-09-15 | IT Operations | 15,000.00 | 14,975.00 | 25 | On Track
Post-Implementation Review | 2024-09-16 | 2024-10-31 | Project Manager & Stakeholders | 5,000.00 | 4,950.00 | 50 | On Track