## Worksheet
Task | Start Date | End Date | Responsible Party | Budget Allocation (USD) | Actual Cost (USD) | Variance | Status
Project Initiation & Feasibility Study | 2024-03-01 | 2024-03-15 | Project Manager | 50,000 | 48,500 | +1,500 (Under budget) | On Track
Requirement Gathering & Analysis | 2024-03-16 | 2024-04-10 | Business Analysts | 65,000 | 64,200 | +800 (Under budget) | On Track
Design Phase (UI/UX & Architecture) | 2024-04-11 | 2024-05-15 | Design Team | 90,000 | 88,400 | +1,600 (Under budget) | On Track
Development & Coding | 2024-05-16 | 2024-07-30 | Development Team | 450,000 | 425,000 | +25,000 (Under budget) | On Track
Testing & Quality Assurance | 2024-08-01 | 2024-08-25 | QA Team | 75,000 | 74,800 | +200 (Under budget) | On Track
Deployment & Go-Live | 2024-08-26 | 2024-08-31 | IT Operations | 25,000 | 24,500 | +500 (Under budget) | On Track
Post-Deployment Review & Reporting | 2024-09-01 | 2024-09-15 | Project Manager | 30,000 | 29,800 | +200 (Under budget) | On Track