## Worksheet
Task | Start Date | End Date | Responsible Party | Budget Allocation | Status
Project Initiation | 01/01/2024 | 01/15/2024 | Project Manager | $5,000 | Completed
Requirements Gathering | 01/16/2024 | 02/15/2024 | Business Analysts | $8,000 | In Progress
Design Phase | 02/16/2024 | 03/31/2024 | Design Team | $12,000 | Planned
Development Phase | 04/01/2024 | 06/30/2024 | Development Team | $50,000 | Not Started
Testing & QA | 07/01/2024 | 07/31/2024 | QA Team | $15,000 | Planned
Deployment & Go-Live | 08/01/2024 | 08/15/2024 | Operations Team | $7,500 | Not Started
Post-Implementation Review | 08/16/2024 | 08/31/2024 | Project Manager | $3,500 | Planned