## Worksheet
Task | Start Date | End Date | Responsible | Budget (USD) | Status | Cost Variance
Market Research | 2024-03-01 | 2024-03-15 | Alex Chen | 15,000 | On Track | 200
Product Design | 2024-03-16 | 2024-04-10 | Samira Patel | 30,000 | On Track | -500
Development Phase | 2024-04-11 | 2024-06-30 | Jordan Lee | 120,000 | At Risk | +3,200
QA & Testing | 2024-07-01 | 2024-07-31 | Taylor Kim | 15,000 | On Track | 0
Launch & Marketing | 2024-08-01 | 2024-08-31 | Morgan Reed | 50,000 | Pending Approval | -