## Worksheet
Task | Start Date | End Date | Responsible Team | Budget Allocated ($) | Actual Cost ($) | Variance ($) | Status
Project Initiation | 01/01/2024 | 01/15/2024 | Project Management Team | 15,000 | 14,800 | 200 | On Track
Requirements Gathering | 01/16/2024 | 02/28/2024 | Business Analysis Team | 30,000 | 31,500 | -1,500 | On Track
Design Phase | 03/01/2024 | 04/15/2024 | Design Team | 50,000 | 49,200 | 800 | On Track
Development Phase | 04/16/2024 | 07/31/2024 | Engineering Team | 150,000 | 148,500 | +1,500 | On Track
Testing & QA | 08/01/2024 | 09/15/2024 | QA Team | 40,000 | 39,800 | 200 | On Track
Deployment & Go-Live | 09/16/2024 | 09/30/2024 | Operations Team | 15,000 | 14,950 | 50 | On Track