## Worksheet
Task | Start Date | End Date | Responsible Party | Budget Allocation ($) | Actual Cost ($) | Variance ($) | Status
Project Initiation | 2024-01-01 | 2024-01-15 | Project Manager | 5,000.00 | 4,800.00 | 200 | On Track
Requirements Gathering | 2024-01-16 | 2024-02-28 | Business Analysts | 15,000.00 | 14,750.00 | 250 | On Track
Design Phase | 2024-03-01 | 2024-04-15 | Design Team | 25,000.00 | 24,900.00 | 100 | On Track
Development Phase | 2024-04-16 | 2024-07-31 | Software Engineers | 85,000.00 | 83,250.00 | +1,750.00 | On Track
Testing & Quality Assurance | 2024-08-01 | 2024-09-15 | QA Team | 12,000.00 | 11,850.00 | 150 | On Track
Deployment & Go-Live | 2024-09-16 | 2024-09-30 | Operations Team | 5,000.00 | 5,100.00 | -100 | On Track
Post-Launch Review | 2024-10-01 | 2024-10-15 | Project Manager & Stakeholders | 3,000.00 | 3,050.00 | -50 | On Track
Total Budget Allocation: $150,000.00
Template Version – Purpose: Cost Control ¦ Template Type: Project Timeline