## Worksheet
Project Name | Project Code | Start Date | End Date | Budget (USD) | Allocated Funds (USD) | Remaining Budget (USD) | Actual Expenditure (USD) | Variance (USD) | Variance % | Cost Control Status | Last Review Date | Responsible Manager
Digital Transformation Initiative | DTI-2024 | 2024-03-01 | 2025-09-30 | 5,000,000 | 4,256,789 | 743,211 | 4,312,500 | -68,211 | -1.36% | On Track | 2024-07-15 | Sarah Johnson
Cloud Infrastructure Upgrade | CIU-2024 | 2024-05-10 | 2025-03-31 | 1,800,000 | 1,678,954 | 121,046 | 1,723,500 | -44,546 | -2.47% | On Track | 2024-08-01 | David Chen
Customer Experience Platform Launch | CEP-L2024 | 2024-06-15 | 2025-12-31 | 3,500,000 | 3,489,123 | 10,877 | 3,625,450 | +125,450 | +3.6% | At Risk | 2024-09-20 | Lisa Park
Supply Chain Optimization Project | SCO-2024 | 2024-04-05 | 2025-11-30 | 2,100,000 | 2,134,567 | -34,567 | 2,189,000 | +54,433 | +2.6% | Over Budget | 2024-10-10 | Michael Reed