## Worksheet
Project Name | Budget (USD) | Actual Spend (USD) | Variance (USD) | Variance % | Status | Last Update | Cost Control Actions Taken
Phase I Development | 500,000 | 485,200 | +14,800 | +2.96% | On Track | 2024-03-15 | Regular monthly reviews; procurement optimization
User Interface Redesign | 250,000 | 268,900 | -18,900 | -7.56% | At Risk | 2024-03-12 | Scope adjustment; reallocation of design budget
Cloud Migration Project | 750,000 | 723,500 | +26,500 | +3.53% | On Track | 2024-03-14 | Vendor negotiation; phased rollout strategy
Mobile App Integration | 300,000 | 315,700 | -9,300 | -3.1% | Over Budget | 2024-03-10 | Additional third-party licensing; timeline extension approved