## Project Tracker - Cost Control
Project Tracker - Cost Control (Personal Use)
Project Name | Start Date | End Date | Budget (USD) | Actual Spend (USD) | Variance (USD) | Status th> | Notes th>
Website Redesign | 2024-01-15 | 2024-03-30 | 15,000.00 | 13,850.00 |  | +1,150.00 | On Track | No major deviations.
Office Equipment Upgrade | 2024-02-01 | 2024-03-15 | 8,500.00 | 9,150.00 | -650 | Budget Overrun | Unexpected software license costs.
Marketing Campaign Launch | 2024-01-20 | 2024-04-30 | 12,000.00 | 11,750.00 | 250 | On Track | Campaign performance above target.
Data Center Migration | 2024-03-10 | 2024-05-31 | 35,000.00 | 36,875.00 | -1,875.00 | Budget Overrun | Extended downtime and third-party delays.