## Worksheet
Task ID | Task Description | Budget Assigned ($) | Actual Cost ($) | Variance ($) | Status | Start Date | End Date | Responsible Person | Review Cycle (Weeks)
T-001 | Design Phase Finalization | 50,000.00 | 48,250.00 | +1,750.00 | On Track | 2023-10-01 | 2023-11-15 | Alice Johnson | 4
T-002 | Procurement of Materials | 85,000.00 | 92,450.00 | -7,450.00 | At Risk | 2023-11-20 | 2024-01-31 | Bob Smith | 6
T-003 | Development & Testing | 120,000.00 | 115,675.00 | +4,325.00 | On Track | 2024-02-01 | 2024-05-31 | Carol Davis | 16
T-004 | Training & Deployment | 30,000.00 | 28,150.00 | +1,850.00 | On Track | 2024-06-15 | 2024-07-30 | David Lee | 8
Total Budget |  |  |  |  | 385,000.00 | Actual Total Spent |  |  |  | 384,525.00