## Worksheet
Task | Start Date | End Date | Budget Allocation | Actual Cost | Variance | Status | Responsible Party
Project Initiation | 2024-01-01 | 2024-01-15 | $50,000 | $48,750 | +$1,250 (Under Budget) | On Track | Project Manager
Design Phase | 2024-01-16 | 2024-03-31 | $150,000 | $148,500 | +$1,500 (Under Budget) | On Track | Design Lead
Development & Testing | 2024-04-01 | 2024-07-30 | $300,000 | $315,250 | -$15,250 (Over Budget) | At Risk | Engineering Team
Deployment & Training | 2024-08-01 | 2024-08-31 | $75,000 | $74,950 | +$50 (Under Budget) | On Track | Operations Lead
Post-Implementation Review | 2024-09-01 | 2024-09-30 | $25,000 | $24,850 | +$150 (Under Budget) | On Track | Finance & Compliance Officer