## Worksheet
Task ID | Task Description | Start Date | End Date | Budget Allocation ($) | Actual Cost ($) | Variance ($) | Status | Responsible Person | Review Frequency | Notes
T001 | Project Initiation & Feasibility Study | 2024-03-01 | 2024-03-15 | 50,000.00 | 48,750.00 |  | +1,250.00 | On Track | Jane Smith | Bi-weekly | Initial scope confirmed; budget under control.
T002 | Design Phase - UI/UX Development | 2024-03-16 | 2024-04-30 | 85,000.00 | 82,950.00 | +2,050.00 | On Track | Alex Johnson | Weekly | Design mockups approved by stakeholders.
T003 | Development & Coding Phase | 2024-05-01 | 2024-07-15 | 375,000.00 | 368,250.00 | +6,750.00 | On Track | Mark Lee | Bi-weekly | No critical delays; progress aligned with plan.
T004 | Testing & Quality Assurance | 2024-07-16 | 2024-08-31 | 65,000.00 | 69,350.00 | -4,350.00 | On Track (slight overage) | Sarah Kim | Weekly | Minor regression issues found; resolved promptly.
T005 | Deployment & Go-Live | 2024-09-01 | 2024-09-15 | 35,000.00 | 34,875.00 | 125 | On Track | David Brown | Daily | Go-live completed without major incidents.