## Worksheet
Task / Activity | Planned Start Date | Planned End Date | Budget (USD) | Actual Cost (USD) | Variance (USD) | Status | Responsible Party
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 5,000 | 4,850 | 150 | On Track | Project Manager
Market Research Phase | 2024-03-05 | 2024-03-15 | 15,000 | 14,200 | 800 | On Track | Research Lead
Design & Prototyping | 2024-03-16 | 2024-04-10 | 35,000 | 38,500 | -3,500 | Over Budget | Design Team
Development Phase (Phase 1) | 2024-04-11 | 2024-05-31 | 75,000 | 72,300 | +2,700 | On Track | Engineering Lead
Testing & Quality Assurance | 2024-06-01 | 2024-06-30 | 18,000 | 17,950 | 50 | On Track | QA Manager
Final Review & Approval | 2024-07-01 | 2024-07-05 | 8,000 | 8,150 | -150 | On Track | Executive Sponsor
Total Planned Budget: |  |  | 165,000 | 172,950 | -7,950 | Overall Variance: Over Budget (USD)