## Worksheet
Task | Start Date | End Date | Assigned To | Budget (USD) | Actual Cost (USD) | Variance | Status | Priority
Market Research & Analysis | 2024-04-01 | 2024-04-15 | Jane Doe | 15,000 | 14,200 | +800 (Under Budget) | On Track | High
Product Design & Prototyping | 2024-04-16 | 2024-05-30 | Mark Smith | 60,000 | 58,500 | +1,500 (Under Budget) | On Track | High
Supplier Onboarding & Negotiation | 2024-05-01 | 2024-05-25 | Lisa Chen | 18,000 | 19,500 | -1,500 (Over Budget) | At Risk | Medium
Quality Assurance Testing | 2024-06-01 | 2024-06-30 | David Kim | 12,000 | 11,800 | +200 (Under Budget) | On Track | Medium
Launch Campaign & Marketing | 2024-07-01 | 2024-08-15 | Sarah Lee | 90,000 | 85,000 | +5,000 (Under Budget) | On Track | High