## Worksheet
Task | Planned Start Date | Planned End Date | Budget (USD) | Actual Cost (USD) | Variance | Status | Responsible Manager
Project Initiation | 2024-03-01 | 2024-03-15 | 15,000 | 14,850 | +150 (Under Budget) | On Track | John Smith
Design Phase | 2024-03-16 | 2024-04-30 | 50,000 | 49,750 | +250 (Under Budget) | On Track | Anna Lee
Development Phase | 2024-05-01 | 2024-07-31 | 180,000 | 178,500 | +1,500 (Under Budget) | On Track | Marcus Taylor
Testing & QA | 2024-08-01 | 2024-08-31 | 35,000 | 36,250 | -1,250 (Over Budget) | At Risk | Sarah Kim
Deployment & Training | 2024-09-01 | 2024-09-30 | 25,000 | 25,150 | -150 (Over Budget) | At Risk | David Wong
Total Budget | [6 empty] | $305,000
Total Actual Cost | [6 empty] | $304,450
Overall Variance (USD) | [6 empty] | 550