## Worksheet
Project Phase | Task Description | Start Date | End Date | Budget Allocation (USD) | Actual Spend (USD) | Variance (USD) | Status | Responsible Team
Initiation | Feasibility Study & Stakeholder Analysis | 2024-03-01 | 2024-03-15 | 5,000.00 | 4,850.00 | 150 | On Track | Project Office
Planning | Resource Planning & Risk Assessment | 2024-03-16 | 2024-04-10 | 15,000.00 | 14,750.00 | 250 | On Track | Operations Team
Execution | Development & Testing Phase | 2024-04-11 | 2024-07-30 | 75,000.00 | 68,950.00 | +6,050.00 | On Track (Minor Delay) | Engineering Team
Monitoring & Control | Monthly Financial Review & Adjustments | 2024-08-01 | 2024-12-31 | 50,000.00 | 49,550.00 | 450 | On Track | Finance & Compliance Team
Closure | Final Audit & Handover Process | 2025-01-01 | 2025-01-31 | 8,000.00 | 7,980.00 | 20 | On Track | Project Closure Team
Total Budget |  |  |  | $103,000.00 | $103,875.00 | $875.00 (Overrun) | Overall Status: Controlled with Minor Overrun