## Worksheet
Project Phase | Start Date | End Date | Budget (USD) | Actual Cost (USD) | Variance (USD) | Status | Responsible Team
Planning | 2024-01-15 | 2024-02-14 | 50,000 | 48,750 | +1,250 | On Track | Project Management Office
Design & Development | 2024-02-15 | 2024-05-31 | 300,000 | 295,600 | +4,400 | On Track | Engineering Team
Testing & Validation | 2024-06-01 | 2024-07-31 | 75,000 | 73,250 | +1,750 | On Track | QA Team
Deployment & Go-Live | 2024-08-01 | 2024-08-31 | 50,000 | 52,150 | -2,150 | Over Budget | Operations Team
Post-Implementation Review | 2024-09-01 | 2024-09-30 | 15,000 | 14,850 | 150 | On Track | Finance & Compliance
Total Project Cost: |  |  | 490,000 | 485,550 | +4,450 | Overall On Track (with minor variance)