## Worksheet
Task | Responsible Team | Start Date | End Date | Budget Allocation ($) | Actual Spend ($) | Variance ($) | Status
Project Planning & Scope Finalization | Project Management Team | 2024-03-01 | 2024-03-15 | 5,000 | 4,850 | 150 | On Track
Design & Prototyping Phase | Engineering Team | 2024-03-16 | 2024-04-30 | 15,000 | 14,750 | 250 | On Track
Development & Coding | Software Development Team | 2024-05-01 | 2024-07-15 | 40,000 | 39,200 | 800 | On Track
Testing & Quality Assurance | QA Team | 2024-07-16 | 2024-08-31 | 10,000 | 9,950 | 50 | On Track
Deployment & Launch | Operations Team | 2024-09-01 | 2024-09-15 | 8,000 | 7,850 | 150 | On Track
Total Budget |  |  |  | 88,000 | 86,600 | +1,400 | Overall Status: On Track