## Worksheet
Task ID | Task Description | Budget Allocated | Actual Cost | Variance (Actual - Budget) | Status | Owner | Last Updated
T001 | Market Research Survey Deployment | $15,000 | $13,800 | -$1,200 | On Track | Jane Doe | 2024-04-15
T002 | Supplier Contract Negotiation | $25,000 | $28,500 | +$3,500 | Over Budget | John Smith | 2024-04-14
T003 | Product Development Phase 1 | $120,000 | $112,300 | -$7,700 | On Track | Alex Chen | 2024-04-13
T004 | Quality Assurance Testing | $30,000 | $29,850 | -$150 | On Track | Sara Lee | 2024-04-12