## Worksheet
Task ID | Task Description | Assigned To | Start Date | End Date | Budget Allocation | Actual Cost | Variance | Status
TC-001 | Material Procurement for Building Phase | John Smith | 2024-03-15 | 2024-04-30 | $50,000.00 | $48,750.00 | +$1,250.00 | On Track
TC-002 | <Design Review and Finalization | Sarah Lee | 2024-03-20 | 2024-04-15 | $35,000.00 | $37,150.00 | -$2,150.00 | Over Budget
TC-003 | Labour Cost Tracking (Site Supervision) | Mike Johnson | 2024-03-18 | 2024-05-10 | $45,000.00 | $43,950.00 | +$1,050.00 | On Track
TC-004 | Equipment Maintenance Schedule | Emma Brown | 2024-03-25 | 2024-06-30 | $18,000.00 | $17,650.00 | +$350.00 | On Track