## Worksheet
Task ID | Task Description | Responsible Person | Start Date | End Date | Budget Allocated (USD) | Actual Cost (USD) | Variance (USD) | Status | Review Date
T001 | Procurement of Office Supplies | John Smith | 2024-03-15 | 2024-03-31 | 500 | 485.5 | 14.5 | Completed | 2024-03-31
T002 | IT Infrastructure Upgrade | Sarah Lee | 2024-04-01 | 2024-05-30 | 15,000.00 | 14,750.33 | 249.67 | In Progress | 2024-04-15
T003 | Employee Training Program | Michael Chen | 2024-04-10 | 2024-06-30 | 8,500.00 | 8,756.99 | -256.99 | Pending Review | 2024-05-15
T004 | Marketing Campaign Launch | Linda Park | 2024-05-15 | 2024-06-30 | 12,000.00 | 11,899.50 | 100.5 | In Progress | 2024-06-15