## Worksheet
Task ID | Task Description | Responsible Person | Start Date | End Date | Estimated Cost | Actual Cost | Cost Variance | Status | Priority Level | Budget Allocation | Review Date
TC-001 | Procurement of Office Supplies | Jane Smith | 2024-03-15 | 2024-03-25 | $1,500.00 | $1,485.00 | +$15.00 | On Track | High | $2,000.00 | 2024-03-31
TC-002 | Software Licensing Renewal | Mike Johnson | 2024-04-01 | 2024-04-15 | $3,850.00 | $3,925.00 | -$75.00 | At Risk | High | $4,000.00 | 2024-04-16
TC-003 | Facility Maintenance Upgrade | Sarah Lee | 2024-05-01 | 2024-06-30 | $15,000.00 | $14,750.00 | +$250.00 | On Track | Moderate | $16,500.00 | 2024-06-31
TC-004 | Travel Expense Reconciliation | David Kim | 2024-03-18 | 2024-03-31 | $950.00 | $958.50 | -$8.50 | Completed | Low | $1,200.00 | 2024-04-15