## Worksheet
Task ID | Task Description | Responsible Person | Start Date | End Date | Budget Allocation | Actual Cost | Variance (Actual - Budget) | Status | Notes
TC-001 | Procurement of Office Supplies | John Smith | 2024-03-15 | 2024-03-31 | $1,500.00 | $1,450.00 | -$50.00 | On Track | Delivered on time; minor savings achieved.
TC-002 | IT Infrastructure Upgrade | Emma Johnson | 2024-04-01 | 2024-05-15 | $15,000.00 | $16,200.00 | +$1,200.00 | Over Budget | Additional vendor costs due to delays.
TC-003 | Employee Training Program | Mike Taylor | 2024-03-20 | 2024-04-15 | $8,500.00 | $8,500.00 | $0.00 | On Budget | All sessions completed as planned.
TC-004 | Office Space Renovation | Sarah Lee | 2024-05-01 | 2024-06-30 | $35,000.00 | $37,895.00 | +$2,895.00 | Over Budget | Unexpected design changes increased costs.