## Worksheet
Task ID | Task Description | Assigned To | Start Date | End Date | Estimated Cost | Actual Cost | Budget Remaining | Status | Priority
T001 | Procure new office equipment | Jane Smith | 2024-03-15 | 2024-04-15 | $8,500.00 | $7,950.00 | $550.00 | Completed | High
T002 | Review quarterly expense reports | Mark Johnson | 2024-03-20 | 2024-04-10 | $3,200.00 | $3,185.50 | $145.50 | In Progress | Medium
T003 | Renew software subscription licenses | Sarah Lee | 2024-03-25 | 2024-04-30 | $6,800.00 | $6,800.00 | $0.00 | Planned | High
T004 | Conduct cost-benefit analysis of new system | David Kim | 2024-03-18 | 2024-05-15 | $9,500.00 | $3,250.00 | $6,250.00 | Pending Approval | High
T005 | Reduce vendor overhead costs by 15% | Linda Wong | 2024-03-30 | 2024-06-30 | $15,000.00 | $12,750.00 | $2,250.00 | Active | Medium