## Worksheet
Task ID | Task Description | Assigned To | Start Date | Due Date | Budget (USD) | Actual Cost (USD) | Status | Variance (%) | Action Required
T-001 | Procurement of office supplies | Jane Smith | 05/01/2024 | 05/15/2024 | 850 | 780.5 | On Track | +8.18% | Review next quarter budget
T-002 | Contract review with vendor XYZ | Mark Johnson | 05/10/2024 | 06/05/2024 | 1,500.00 | 1,650.00 | Over Budget | -9.00% | Submit variance report
T-003 | Facility renovation planning | Lisa Chen | 05/08/2024 | 07/10/2024 | 5,000.00 | 4,850.00 | On Track | +3.00% | Update project timeline
T-004 | IT infrastructure upgrade | Robert Kim | 05/14/2024 | 08/30/2024 | 15,000.00 | 16,350.00 | Over Budget | -7.00% | Conduct cost audit
T-005 | Employee training program | Sophia Davis | 05/03/2024 | 06/15/2024 | 3,500.00 | 3,450.00 | On Track | +1.43% | Submit completion report