## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Budget Allocation | Actual Spend | Variance | Status | Priority
T001 | Market Research Survey | Jane Smith | 2024-03-01 | 2024-03-15 | $5,000 | $4,800 | +$200 (Under) | On Track | Medium
T002 | Vendor Contract Negotiation | John Doe | 2024-03-10 | 2024-04-05 | $15,000 | $16,200 | -$1,200 (Over) | At Risk | High
T003 | Development Sprint Planning | Sarah Lee | 2024-03-18 | 2024-04-15 | $30,000 | $31,500 | -$1,500 (Over) | On Hold | High
T004 | Quality Assurance Testing | Mike Chen | 2024-04-01 | 2024-04-30 | $10,000 | $9,750 | +$250 (Under) | Completed | Medium
Total Budget Allocated |  |  |  |  | $60,000 | $62,450 | -$2,450 (Over) | Cost Control Summary