## Worksheet
Task ID | Task Description | Assigned To | Start Date | End Date | Budget (USD) | Actual Cost (USD) | Variance (USD) | Status | Cost Control Actions
TC-001 | Procure Monthly Supplies | Jane Doe | 2023-10-01 | 2023-10-31 | 5,000.00 | 4,850.00 | 150 | On Track | Review supplier pricing quarterly.
TC-002 | Staff Training Session | John Smith | 2023-10-15 | 2023-10-18 | 3,500.00 | 3,475.00 | 25 | Completed | No action required.
TC-003 | Equipment Maintenance | Alice Brown | 2023-10-05 | 2023-10-12 | 4,200.00 | 4,950.00 | -750 | Over Budget | Re-evaluate vendor and adjust schedule.
TC-004 | Monthly Financial Report Review | Robert Lee | 2023-10-25 | 2023-10-30 | 2,800.00 | 2,750.00 | 50 | In Progress | Monitor for cost overruns.
TC-005 | Office Renovation (Phase 1) | Sarah Chen | 2023-11-01 | 2023-11-30 | 8,500.00 | 8,465.00 | 35 | On Track | Ensure compliance with budget constraints.