## Worksheet
Task ID | Task Description | Assigned To | Start Date | End Date | Budget Allocation | Actual Cost | Variance (Actual - Budget) | Status | Approval Status
TC-001 | Procure office supplies | Alice Johnson | 2024-03-15 | 2024-03-25 | $1,500.00 | $1,480.00 | $20.00 (Under) | Completed | Approved
TC-002 | Review monthly operational expenses | Bob Smith | 2024-03-18 | 2024-04-15 | $5,000.00 | $5,350.00 | $350.00 (Over) | In Progress | Pending Review
TC-003 | Update vendor cost analysis report | Charlie Brown | 2024-03-20 | 2024-04-10 | $3,800.00 | $3,750.00 | $50.00 (Under) | Planned | Approved
TC-004 | Conduct cost-benefit analysis for new software | Diana Prince | 2024-03-25 | 2024-05-15 | $18,000.00 | $17,650.00 | $350.00 (Under) | Not Started | Approved
Cost Control Summary | [8 empty] | Total Variance: $1,050.00 (Under)