## Worksheet
Task | Responsible Party | Budget Allocated (USD) | Actual Cost (USD) | Variance | Status | Due Date
Material Procurement | Procurement Manager | $50,000 | $48,500 | +$1,500 (Under Budget) | Completed | 2024-03-15
Labor Allocation | Project Lead | $75,000 | $78,200 | -$3,200 (Over Budget) | In Progress | 2024-04-30
Equipment Rental | Finance Officer | $20,000 | $19,800 | +$200 (Under Budget) | Completed | 2024-03-30
Travel Expenses | Operations Team | $8,000 | $7,600 | +$400 (Under Budget) | Completed | 2024-03-20
Contingency Fund | Finance Director | $5,000 | $4,500 | +$500 (Under Budget) | Available | N/A