## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Budget (USD) | Actual Cost (USD) | Status | Variance (%) | Remarks
T001 | Initial Project Planning | Jane Doe | 2024-03-01 | 2024-03-15 | 15,000.00 | 14,250.00 | On Track | -5.0% | Completed ahead of schedule.
T002 | Procurement of Materials | John Smith | 2024-03-16 | 2024-04-10 | 35,000.00 | 36,850.00 | Over Budget | +5.3% | Supplier delay caused cost overrun.
T003 | Design Finalization | Lisa Chen | 2024-04-11 | 2024-05-05 | 45,000.00 | 43,750.00 | On Track | -2.8% | Design approved early.
T004 | Staff Training & Onboarding | Mike Brown | 2024-05-06 | 2024-05-18 | 12,000.00 | 11,950.00 | On Track | -0.4% | All trainees completed successfully.