## Worksheet
Task ID | Task Description | Assigned To | Start Date | End Date | Budget Allocated | Actual Cost | Variance | Status | Action Required
T001 | Design Phase Finalization | John Smith | 2024-03-01 | 2024-03-15 | $15,000 | $14,250 | $750 (Under Budget) | On Track | Review progress weekly
T002 | Procurement of Materials | Sarah Lee | 2024-03-16 | 2024-04-10 | $35,000 | $38,500 | $3,500 (Over Budget) | At Risk | Re-evaluate supplier options
T003 | Employee Training Program | Mike Chen | 2024-03-20 | 2024-04-15 | $8,000 | $7,950 | $50 (Under Budget) | On Track | Confirm completion by end of month
T004 | System Integration Testing | Lisa Wong | 2024-04-01 | 2024-05-31 | $50,000 | $52,300 | $2,300 (Over Budget) | On Hold | Delay until next phase approval