## Worksheet
Task ID | Task Name | Department | Assigned To | Start Date | End Date | Budget (USD) | Actual Cost (USD) | Variance (USD) | Status
T001 | Project Initiation Workshop | Finance | Sarah Johnson | 2024-03-15 | 2024-03-20 | 5,000.00 | 4,850.00 | 150 | Completed
T002 | Supplier Cost Audit | Procurement | Michael Chen | 2024-03-21 | 2024-04-10 | 15,000.00 | 14,250.00 | 750 | In Progress
T003 | Office Equipment Replacement | Operations | Linda Patel | 2024-03-18 | 2024-04-05 | 8,500.00 | 8,625.00 | -125 | Completed
T004 | Energy Efficiency Upgrade | Facilities | David Kim | 2024-04-01 | 2024-05-15 | 30,000.00 | 29,750.00 | 250 | Planned