## Worksheet
Task ID | Task Description | Assigned To | Start Date | Due Date | Budget Allocated | Actual Cost | Variance | Status | Remarks
T001 | Finalize project scope document | Sarah Johnson | 2024-03-15 | 2024-03-25 | $5,000 | $4,800 | +$200 (Under) | On Track | Scope approved by stakeholders.
T002 | Conduct cost-benefit analysis | Michael Chen | 2024-03-18 | 2024-04-05 | $8,500 | $9,100 | -$600 (Over) | At Risk | Review with finance team for adjustments.
T003 | Procure equipment and materials | Lisa Patel | 2024-03-20 | 2024-04-10 | $15,000 | $14,750 | +$250 (Under) | On Track | Vendor confirmed; delivery on schedule.
T004 | Monitor weekly spending reports | Team Lead | 2024-03-12 | Ongoing | $0 (Monthly) | $0 | – | Ongoing Monitoring | Daily reports shared in team channel.