## Worksheet
Task ID | Task Description | Assigned To | Start Date | End Date | Estimated Cost | Actual Cost | Cost Variance | Status | Priority
TC-001 | Procure materials for project Phase 1 | John Doe | 2024-03-15 | 2024-04-15 | $15,000.00 | $14,850.00 | +$150.00 | Completed | Medium
TC-002 | Finalize budget allocation for Q2 | Sarah Lee | 2024-03-20 | 2024-04-10 | $8,500.00 | $8,750.00 | -$250.00 | In Progress | High
TC-003 | Review vendor contracts for cost optimization | Michael Brown | 2024-03-18 | 2024-05-15 | $12,000.00 | $11,950.00 | +$50.00 | Planned | Medium
TC-004 | Conduct cost audit for previous quarter | Lisa Chen | 2024-03-25 | 2024-04-30 | $9,800.00 | $9,650.00 | +$150.00 | Completed | Low