## Worksheet
Task ID | Task Description | Responsible Person | Start Date | Due Date | Current Status | Budget Allocated (USD) | Actual Spend (USD) | Variance | Action Required
TC-001 | Procurement of office supplies | Jane Smith | 2024-03-15 | 2024-03-31 | Completed | 500 | 485.5 | -14.5 | No action required
TC-002 | Development of new software moduleMark Johnson | 2024-04-01 | 2024-05-15 | In Progress | 8,000.00 | 6,532.75 | +1,467.25 | Review progress weekly
TC-003 | Office space renovation | Sarah Lee | 2024-03-20 | 2024-06-30 | Pending Approval | 15,000.00 | — | — | Approval needed by end of March
TC-004 | Employee training program launch | David Chen | 2024-04-10 | 2024-05-31 | Not Started | 3,000.00 | — | — | Schedule kickoff meeting