## Worksheet
Date | Task Description | Start Time | End Time | Duration (hrs) | Project/Department | Cost Center | Allocated Budget (USD) | Actual Spend (USD) | Variance (USD) | Status
2024-04-05 | Develop UI Mockups | 09:00 | 12:30 | 3.5 | Product Design | DC-004 | 500 | 480 | 20 | On Track
2024-04-06 | Code Backend API Integration | 10:00 | 17:00 | 7 | Engineering Team | EN-023 | 800 | 795 | 5 | On Track
2024-04-07 | Client Review Meeting | 14:00 | 15:30 | 1.5 | Client Services | CS-009 | 250 | 250 | 0 | On Track
2024-04-08 | Database Optimization | 09:30 | 18:00 | 8.5 | Infrastructure | IT-050 | 950 | 940 | 10 | On Track
2024-04-09 | Final QA Testing | 08:00 | 16:00 | 8 | Quality Assurance | QA-015 | 600 | 595 | 5 | On Track