## Worksheet
Task | Responsibility | Deadline | Status | Estimated Cost | Actual Cost (if any) | Variance
Review monthly expense reports | Finance Team | 2023-10-15 | Completed | $5,000 | $4,800 | +$200 (within budget)
Conduct vendor cost audit | Procurement Team | 2023-10-25 | In Progress | $15,000 | - | -
Implement cost-saving policy in HR operations | HR Manager | 2023-11-10 | Pending Approval | $8,500 | - | -
Monitor utility bills and negotiate rates | Operations Lead | 2023-10-30 | To Do | $4,200 | - | -