## Worksheet
Task | Owner | Due Date | Status | Estimated Cost | Actual Cost | Variance
Review Monthly Budget | Finance Manager | 2023-10-15 | Completed | $5,000 | $4,800 | +$200
Audit Vendor Contracts | Procurement Lead | 2023-10-30 | In Progress | $8,500 | $6,200 | +$2,300
Update Expense Reporting System | IT Department | 2023-11-10 | Pending | $12,000 | - | -
Conduct Cost-Benefit Analysis | Project Manager | 2023-11-05 | Not Started | $9,000 | - | -