## Worksheet
Task | Owner | Due Date | Status | Cost Estimate ($) | Actual Cost ($) | Variance
Review quarterly budget forecast | Finance Team | 2023-09-30 | In Progress | 15,000 | 14,250 | +750 (under)
Conduct supplier cost audit | Purchasing Manager | 2023-10-15 | Not Started | 8,500 | - | -
Implement energy-saving measures in offices | <Operations Lead | 2023-11-05 | Planned | 22,000 | - | -
Review vendor contracts for renegotiation | Legal & Procurement | 2023-10-30 | In Progress | 18,750 | 17,900 | +850 (under)
Monthly cost variance analysis reporting | Finance Analyst | Every Month 5th | Ongoing | - | - | -
Total Estimated Cost |  |  | $64,250