## Worksheet
Task | Assigned To | Priority | Status | Budget Allocated | Actual Cost | Variance | Date Added | Due Date
Review Monthly Expense Reports | Finance Team | High | In Progress | $10,000 | $9,500 | +$500 (Under) | 2024-04-15 | 2024-05-15
Audit Vendor Contracts | Legal Department | High | Not Started | $15,000 | - | - (Pending) | 2024-04-18 | 2024-06-15
Implement Expense Approval Workflow | IT & Operations | Medium | Planned | $20,000 | - | - (Pending) | 2024-04-25 | 2024-07-30
Monthly Budget Reconciliation | Accounting Manager | High | Completed | $8,000 | $8,200 | -$200 (Over) | 2024-04-10 | 2024-05-10