## Worksheet
Advanced Gantt Chart - Data Collection
Task ID | Task Name | Start Date | End Date | Status | Progress (%)
T001 | Define Data Requirements | 2024-12-05 | 2024-12-15 | In Progress
T002 | Design Data Collection Forms | 2024-12-16 | 2024-12-30 | In Progress
T003 | Recruit Data Collectors | 2024-12-18 | 2025-01-05 | Pending
T004 | Train Collection Team | 2025-01-06 | 2025-01-15 | Pending
T005 | Field Data Collection | 2025-01-16 | 2025-02-14 | Not Started
T006 | Data Validation & Cleaning | 2025-02-15 | 2025-03-14 | Not Started
T007 | Data Analysis & Reporting | 2025-03-15 | 2025-04-15 | Not Started
T008 | Final Review & Submission | 2025-04-16 | 2025-04-30 | Not Started
Total Duration: |  |  |  | 10 weeks