## Worksheet
Data Collection - Gantt Chart (Client View)
Task ID | Task Name | Start Date | End Date | Status | Progress (%)
001 | Initial Requirements Gathering | 2024-04-15 | 2024-04-30 | In Progress
002 | Client Interviews & Surveys | 2024-05-01 | 2024-05-15 | In Progress
003 | Data Validation & Cleaning | 2024-05-16 | 2024-05-31 | Pending
004 | Database Integration | 2024-06-01 | 2024-06-15 | Pending
005 | Final Reporting & Submission | 2024-06-16 | 2024-06-30 | Pending
006 | Client Review & Approval | 2024-07-01 | 2024-07-15 | Pending
Total Duration: |  |  |  | 2024-04-15 to 2024-07-15