## Worksheet
Daily Gantt Chart - Data Collection
Task ID | Task Name | Start Date (Daily) | End Date (Daily) | Status
T001 | Data Gathering Preparation | 2025-04-05 | 2025-04-05 | In Progress
T002 | Survey Design & Approval | 2025-04-06 | 2025-04-07 | Not Started
T003 | Participant Recruitment | 2025-04-08 | 2025-04-11 | In Progress
T004 | Data Collection - Field Work | 2025-04-12 | 2025-04-15 | Not Started
T005 | Data Entry & Validation | 2025-04-16 | 2025-04-18 | Not Started
T006 | Data Analysis Phase 1 | 2025-04-19 | 2025-04-21 | Not Started
T007 | Milestone: Initial Findings Review | 2025-04-21 | 2025-04-21 | Milestone
T008 | Data Analysis Phase 2 & Reporting | 2025-04-22 | 2025-04-25 | Not Started
T009 | Final Report Submission | 2025-04-26 | 2025-04-26 | Milestone
Gantt Chart View (Daily Scale)
T001 - PrepT002 - Survey DesignT003 - RecruitmentT004 - Field WorkT005 - Data EntryT006 - Analysis Phase 1T007 - Findings ReviewT008 - Analysis Phase 2T009 - Report Submission
Note: This daily Gantt chart is for data collection purposes. Dates are based on a working day format (Monday to Friday).