## Worksheet
Data Collection Gantt Chart - Data Version
Task | Start Date | End Date | Duration (Days) | Status
Define Data Collection Scope | 2024-01-05 | 2024-01-10 | 6 | Completed
Develop Data Collection Instruments | 2024-01-11 | 2024-01-18 | 8 | In Progress
Recruit Data Collectors | 2024-01-19 | 2024-01-25 | 7 | In Progress
Conduct Pilot Testing | 2024-01-26 | 2024-01-31 | 6 | Not Started
Full-Scale Data Collection | 2024-02-01 | 2024-03-15 | 44 | Not Started
Data Validation & Cleaning | 2024-03-16 | 2024-03-31 | 16 | Not Started
Data Analysis Preparation | 2024-04-01 | 2024-04-15 | 15 | Not Started