## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (days) | Status
TASK001 | Data Collection Planning | 2023-10-01 | 2023-10-05 | 5
TASK002 | Define Data Requirements | 2023-10-06 | 2023-10-10 | 5
TASK003 | Develop Survey Instruments | 2023-10-11 | 2023-10-15 | 5
TASK004 | Recruit Participants | 2023-10-16 | 2023-10-25 | 10
TASK005 | Conduct Data Collection Sessions | 2023-10-26 | 2023-11-15 | 20
TASK006 | Data Validation & Cleaning | 2023-11-16 | 2023-11-25 | 10
TASK007 | Finalize Data Repository | 2023-11-26 | 2023-11-30 | 5
TASK008 | Report Preparation | 2023-12-01 | 2023-12-15 | 15
Overall Project Timeline |  |  |  | 60 days
This Gantt Chart is designed for Data Collection purposes. Status indicators reflect progress as of current date.