## Worksheet
Extended Gantt Chart Template - Data Collection
Task ID | Task Name | Start Date | End Date | Duration (Days) | Progress (%)
TC-01 | Data Requirements Definition | 2023-10-01 | 2023-10-07 | 7
TC-02 | Survey Design & Validation | 2023-10-08 | 2023-10-14 | 7
TC-03 | Participant Recruitment | 2023-10-15 | 2023-10-28 | 14
TC-04 | Data Collection Phase I (Pilot) | 2023-10-29 | 2023-11-05 | 7
TC-05 | Data Collection Phase II (Full Scale) | 2023-11-06 | 2023-11-28 | 23
TC-06 | Data Validation & Cleaning | 2023-11-29 | 2023-12-15 | 17
M-01 | Pilot Study Completion | 2023-11-05 | 2023-11-05 | —
M-02 | Full Data Collection Complete | 2023-11-28 | 2023-11-28 | —
TC-07 | Data Analysis Preparation | 2023-12-16 | 2024-01-05 | 19
TC-08 | Statistical Analysis | 2024-01-06 | 2024-01-31 | 26
TC-09 | Report Drafting & Review | 2024-02-01 | 2024-02-15 | 15
M-03 | Final Report Submission | 2024-02-15 | 2024-02-15 | —
Note:This Gantt chart template is designed for data collection purposes with an extended view. Progress percentages are illustrative and can be updated as needed.