## Worksheet
Data Collection Gantt Chart
Large Business Template • Purpose: Data Collection • Version: 2024
Task Name | Start Date | End Date | Progress | Responsible Team / Owner
Define Data Collection Requirements | 2024-04-01 | 2024-04-15 |  | Business Analysts
Design Data Collection Forms | 2024-04-16 | 2024-05-10 |  | UX Design Team
Develop Data Collection Platform | 2024-05-11 | 2024-06-30 |  | Software Development
Test Data Collection Workflow | 2024-07-01 | 2024-07-15 |  | QA Team
Go-Live: Launch Data Collection System | 2024-07-16 | 2024-07-16 |  | Project Manager
Train Internal Users | 2024-07-17 | 2024-07-31 |  | Training Department
Collect Initial Data Sets | 2024-08-01 | 2024-08-31 |  | Data Analysts
First Data Review Meeting | 2024-09-15 | 2024-09-15 |  | Executive Team
Optimize Collection Process | 2024-10-01 | 2024-10-31 |  | Process Improvement
Final Project Sign-Off | 2024-11-30 | 2024-11-30 |  | Project Sponsor
Total Duration | 2024-04-01 to 2024-11-30 |  | Overall Progress: 67% | Project Status: On Track