## Worksheet
Manager View Gantt Chart - Data Collection
Task ID | Task Name | Start Date | End Date | Status | Progress (%)
P01 | Define Data Collection Scope | 2024-05-01 | 2024-05-10 | Completed
P02 | Identify Data Sources | 2024-05-11 | 2024-05-17 | In Progress
P03 | Create Data Collection Forms | 2024-05-18 | 2024-05-25 | Not Started
P04 | Design Data Validation Rules | 2024-05-26 | 2024-05-31 | Not Started
P05 | Deploy Collection Tools | 2024-06-01 | 2024-06-15 | Not Started
P06 | Collect Data from Field | 2024-06-16 | 2024-07-15 | Not Started
P07 | Data Quality Check | 2024-07-16 | 2024-07-31 | Not Started
M01 | Data Collection Complete | 2024-08-01 | 2024-08-01 | Planned